## 2ND2020 (2)
FDPP form 6- Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
2ND QUARTER, CY 2020
Province, City or Municipality of Zarraga | [6 empty] | June 30,2020
| Program or Project | Location | Total Cost | Date Started | Target | Project Status | Total Cost incured to date | No. Of | Remarks
[5 empty] | Completion Date | % of Completion |  | Extension if any
1 | DA-Goat Prod & Carabao | Zarraga Iloilo | 1080000 | 2015-03-20 | On Going | 87.26% | 1074552 |  | On Going
2 | DSWD SLP -Fin. Asst Small Skill Training | Zarraga Iloilo | 4805329.7 | 2016-07-15 | On Going | 95.75% | 4601115.7 |  | On Going
3 | DA Techno Demo | Zarraga Iloilo | 1500000 | 2017-03-02 | On Going | 60.77% | 1374325 |  | On Going
4 | DILG SGLG PCF 2018 | Zarraga Iloilo | 3200000 | 2018-12-05 | not yet imp. | 62.74% | 2805866.69 |  | On Going
5 | Mun of Zarraga GF LGU CounterpartPISOS | Zarraga Iloilo | 600000 | 2019-05-22 | not yet imp. | 86.67% | 520037.6 |  | On Going
7 | Est. of Pantat Hachery and Marketing Support | Zarraga Iloilo | 250000 | 2019-04-25 | On Going | 70% | 175000 |  | On Going
8 | local Access Road Jalaud | Zarraga Iloilo | 10986000 | 2019-10-09 | On Going | 37.56% | 6719614.78 |  | On Going
9 | Incentive SGLG award | Zarraga Iloilo | 2300000 | 2020-01-02 | not yet imp. | 0% | 1567715.86 |  | not yet imp.
10 | Steel Foot bridge sambag balud liloan Balud II (3,2M) | Zarraga Iloilo | 1000000 | 2020-01-01 | not yet imp. | 0% | 697980.1 |  | not yet imp.
11 | Declogging Rehab of Canal Tuburan Sulbod Zarraga(3.2M) | Zarraga Iloilo | 2250000 | 2020-01-01 | not yet imp. | 0% | 1605394.38 |  | not yet imp.
12 | Drainage of funds for Pob.Zarraga | Zarraga Iloilo | 14400000 | 2020-02-01 | not yet imp. | 0% | 0 |  | not yet imp.
13 | Prov. Iloilo Fin Asst for covid 19 | Zarraga Iloilo | 1000000 | 2020-04-01 | implemented | 100% | 1000000 |  | completed
14 | DSWD Reg. 6 Social Pension | Zarraga Iloilo | 6645000 | 2020-04-17 | implemented | 100% | 6645000 |  | completed
15 | Prov. Of Iloilo Fin. Asst | Zarraga Iloilo | 250000 | 2020-04-24 | On Going |  | 249984.6 |  | On Going
16 | Prov. Asst .Augmentation of covid 19 | Zarraga Iloilo | 2498470 | 2020-04-24 | On Going |  | 2498470 |  | On Going
17 | Purchase of Mini Dumptruck | Zarraga Iloilo | 2000000 | 2020-04-30 | implemented | 100% | 2000000 |  | completed
18 | DSWD Reg. 6 Social Pension | Zarraga Iloilo | 2340000 | 2020-04-30 | implemented | 100% | 2340000 |  | completed
19 | Prov. Iloilo Fin Asst for covid 19 | Zarraga Iloilo | 1000000 | 2020-06-01 | On Going |  | 300000 |  | On Going
20 | Prov. Iloilo purchase & instal of 50kva trans | Zarraga Iloilo | 596443.09 | 2020-06-17 | On Going
| TOTAL |  | 43371329.7 |  |  | 66.37% | 28786602.11
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  |  |  | (SGD) ERA P.LERDON |  | (SGD) JOHN H. TARROSA
|  |  |  | OIC Municipal Accountant |  | Municipal Mayor

## IST 2020
FDPP form 6- Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
IST QUARTER, CY 2020
Province, City or Municipality of Zarraga
| Program or Project | Location | Total Cost | Date Started | Target | Project Status | Total Cost incured to date | No. Of | Remarks
[5 empty] | Completion Date | % of Completion |  | Extension if any
1 | DA-Goat Prod & Carabao | Zarraga Iloilo | 1080000 | 2015-03-20 | On Going | 87.26% | 942356 |  | On Going
2 | DSWD SLP -Fin. Asst Small Skill Training | Zarraga Iloilo | 4805329.7 | 2016-07-15 | On Going | 95.75% | 4601115.7 |  | On Going
3 | DA Techno Demo | Zarraga Iloilo | 1500000 | 2017-03-02 | On Going | 60.77% | 911490 |  | On Going
4 | DILG SGLG PCF 2018 | Zarraga Iloilo | 3200000 | 2018-12-05 | not yet imp. | 62.74% | 2007660.82 |  | On Going
5 | Mun of Zarraga GF LGU CounterpartPISOS | Zarraga Iloilo | 600000 | 2019-05-22 | not yet imp. | 86.67% | 520037.6 |  | On Going
7 | Est. of Pantat Hachery and Marketing Support | Zarraga Iloilo | 250000 | 2019-04-25 | On Going | 70% | 175000 |  | On Going
8 | local Access Road Jalaud | Zarraga Iloilo | 10986000 | 2019-10-09 | On Going | 37.56% | 4126863.62 |  | On Going
9 | Incentive SGLG award | Zarraga Iloilo | 2300000 | 2020-01-02 | not yet imp. | 0% | 0 |  | not yet imp.
10 | Steel Foot bridge sambag balud liloan Balud II (3,2M) | Zarraga Iloilo | 1000000 | 2020-01-01 | not yet imp. | 0% |  |  | not yet imp.
11 | Declogging Rehab of Canal Tuburan Sulbod Zarraga(3.2M) | Zarraga Iloilo | 2250000 | 2020-01-01 | not yet imp. | 0% | 0 |  | not yet imp.
12 | Drainage of funds for Pob.Zarraga | Zarraga Iloilo | 14400000 | 2020-02-01 | not yet imp. | 0% | 0 |  | not yet imp.
| TOTAL |  | 42371329.7 |  |  | 31.35% | 13284523.74
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  |  |  | ERA P.LERDON |  | JOHN H. TARROSA
|  |  |  | OIC Municipal Accountant |  | Municipal Mayor