## TO PRINT
FDPP form 6- Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
4TH QUARTER, CY 2019
Province, City or Municipality of Zarraga
| Program or Project | Location | Total Cost | Date Started | Target | Project Status | Total Cost incured to date | No. Of | Remarks
[5 empty] | Completion Date | % of Completion |  | Extension if any
1 | DOH -CHD-CHT | Zarraga Iloilo | 192000 | 2015-12-04 | completed | 100% | 192000 |  | completed
2 | Organic Swine /Native Chicken | Zarraga Iloilo | 500000 | 2015-04-18 | On Going | 59.99% | 299940 |  | On Going
3 | DA-Goat Prod & Carabao | Zarraga Iloilo | 1080000 | 2015-03-20 | On Going | 78.92% | 852356 |  | On Going
4 | Organic Techno Demo& Learning Ctr. | Zarraga Iloilo | 1000000 | 2015-06-11 | On Going | 94.01% | 940059.39 |  | On Going
5 | DSWD SLP -Fin. Asst Small Skill Training | Zarraga Iloilo | 4805329.7 | 2016-07-15 | On Going | 95.88% | 4607115.7 |  | On Going
7 | DA Techno Demo | Zarraga Iloilo | 1500000 | 2017-03-02 | On Going | 55.37% | 830614.1 |  | On Going
8 | Prov. Rehab DBJHS (HE) | Zarraga Iloilo | 250000 | 2018-03-09 | completed | 100% | 250000 |  | completed
9 | Prov. Rehab. Brgy Malunang | Zarraga Iloilo | 300000 | 2018-05-03 | completed | 100% | 300000 |  | completed
10 | EMB 6,Facility and Purchase of SWSF | Zarraga Iloilo | 427500 | 2018-05-04 | completed | 100% | 427500 |  | completed
11 | Prov. Pasalubong Center | Zarraga Iloilo | 1500000 | 2018-06-22 | completed | 100% | 1500000 |  | completed
12 | Prov. Rehab of 21Brgy Roads | Zarraga Iloilo | 2238200 | 2018-05-03 | completed | 100% | 2238200 |  | completed
13 | Prov.Const. Of Talipapa | Zarraga Iloilo | 1380690 | 2018-06-14 | completed | 100% | 1380690 |  | completed
14 | DILG SGLG PCF 2018 | Zarraga Iloilo | 3200000 | 2018-12-05 | On Going | 62.74% | 2007660.82 |  | On Going
15 | Prov Drainage System of ZCES | Zarraga Iloilo | 800000 | 2018-12-17 | completed | 100% | 800000 |  | completed
17 | Mun of Zarraga GF LGU CounterpartPISOS | Zarraga Iloilo | 600000 | 2019-05-22 | On Going | 86.67% | 520037.6 |  | On Going
18 | Est. of Pantat Hachery and Marketing Support | Zarraga Iloilo | 250000 | 2018-04-25 | On Going | 70% | 175000 |  | On Going
19 | local Access Road Jalaud | Zarraga Iloilo | 10986000 | 2019-10-09 | On Going | 14.93% | 1639950 |  | On Going | as of 8/28
| TOTAL |  | 31009719.7 |  |  | 61.15% | 18961123.61
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  | (sgd)GLEZIL MAE S. LOZAÑES |  | (sgd)ERA P.LERDON |  | (sgd)JOHN H. TARROSA
|  | Local Budget Officer |  | OIC Municipal Accountant |  | Municipal Mayor