## Sheet1
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS
for Calendar Year 2020
from April -June 30, 2020
Province, City or Municipality: ZARRAGA, ILOILO
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development (pls list down specific projects)
1.Rehabilitation & Maint. Of Ecological Solid Waste Management Center & Mat. Recovery Facility MRF | Inag.Centro | 1000000 | January 2020 | December 2020 | 0% | 0
2.Improvement of Manpower Development Center (Sports Center) | Covered Gym | 3000000 | January 2020 | December 2020 | 93.56% | 2806666.91 |  | implemented
3.Establishment of Kiosk and Other Park Structures | Plaza & Parks | 1500000 | January 2020 | December 2020 | 81.2% | 1218039.5 |  | implemented
Economic Development(List down specific projects)
1. Improvement/Rehabilitation of | Market | 3545798.46 | January /2020 | December 2020 | 25.18% | 892712.63 |  | implemented
2.0Acquisition of Heavy Equipment | Mun. Wide | 5000455.76 | January /2020 | December 2020 | 29.58% | 1479184.07 |  | implemented
3.Rehabilitation/Improvement of Public Market | Market | 2500000 | January 2020 | December 2020 | 0% | 0
4.Development Project Support Fund | Mun.Wide | 2376133.18 | January 2020 | December 2020 | 0% | 0
Environmental Management (pls list down specific projects)
TOTAL |  | 18922387.4 |  |  |  | 6396603.11
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained
in this document.
______________________________ |  |  |  |  | ____________________
(SGD) GLEZIL MAE S. LOZAÑES |  |  |  |  | (SGD) JOHN H. TARROSA
Local Budget Officer |  |  |  |  | Local Chief Executive